## NOVEMBER
2020-2021 EDUCATION YEAR E-TWINNING LUCK PROJECT ACTIVITY PLAN- NOVEMBER
ACTIVITY | D.APPLICATION | MANNER OF APPLICATION | DATE/DEADLINE | PRODUCT
PROJECT PARTNERS ARE SEARCHED | eTwinning LIVE | PROJECT DESCRIPTION IS MADE ON PARTNERS FORUMS AND SEARCHED FOR MATCHING PARTNERS | OCTOBER 13th DECEMBER 30th | ____________
PROJECT PLAN IS WRITTEN | EXCEL | PROJECT PLAN IS WRITTEN IN DETAILED BY THE FOUNDERS | NOVEMBER 15th | PROJECT PLAN
PROJECT LOGO IS CREATED | EXCEL | A TEMPORARY PROJECT LOGO IS CREATED BY THE FOUNDERS | NOVEMBER22th | PROJECT LOGO
INTRODUCTION VIDEO | POWTOON | PROJECT INTRODUCTION VIDEO IS CREATED BY THE FOUNDERS | NOVEMBER 28th | INTRODUCTION VIDEO
PROJECT BLOG IS CREATED | GOOGLE | PROJECT BLOG IS CREATED BY THE FOUNDERS | NOVEMBER 30th | PROJECT BLOG

## DECEMBER
2020-2021 EDUCATION YEAR E-TWINNING LUCK PROJECT ACTIVITY PLAN -DECEMBER
ACTIVITY | D.APPLICATION | MANNER OF APPLICATION | DEADLINE | PRODUCT
FILL IN THE COMMUNICATION FORM ON PAGES PART AND REGISTER YOURSELF AND YOUR STUDENTS ON MEMBERS PART.PROVIDE THEIR USER NAMES AND PASSWORDS. | TWINSPACE | FILL IN THE REQUIRED INFORMATION FORM, REGISTER 5-20 OF YOUR STUDENTS AND URGE THEM TO LOG IN THE PAGE FREQUENTLY, MAKE COMMENTS, LIKE STUFF ETC. | DECEMBER 1-7 | ______
MEETING WEBINAR for PARTNERS | ZOOM | JOIN IN THE MEETING | DECEMBER 12th | PHOTOS
GET TO KNOW OUR MEMBERS | VIDEORAMA, FLIPGRID YOUTUBE | LET YOUR STUDENTS INTRODUCE THEMSELVES VIA VIDEOS AND DOWNLOAD THEM ON THE MATERIALS PART AND SHARE ON HOME | DECEMBER 7-15 | VIDEOS
PREPARING VISUALS | CANVA, SELF-MADE WORKS | LET YOUR STUDENTS PREPARE SOME VISUALS INTRODUCING OUR PROJECT | DECEMBER 15-21 | PHOTOS, ONLINE WORKS
WHAT DO YOU EXPECT FROM LUCK? | FLIPGRID | LET YOUR STUDENTS LOG IN FLIPGRID VIA GUEST PASSWORD AND RECORD A SHORT VIDEO ANSWERING THE QUESTION | DECEMBER 21-28 | VIDEOS
WEBINAR with PARTNERS | TWINSPACE ONLINE MEETING | WE PLAN OUR NEW YEAR ACTIVITY TOGETHER WITH OUR PARTNERS | DECEMBER 25th | WEBINAR PHOTOS
CHRISTMAS EVENT - MEETING FOR THE MEMBERS | ZOOM-CANVA- POSTERMYWALL | ALL OUR MEMBERS MEET, INTRUDUCE THEMSELVES and TELL THEIR NEW YEAR EXPECTATIONS BY SHOWING THEIR NEW YEAR CARDS | DECEMBER 30th | PHOTOS, NEW YEAR CARDS

## JANUARY
2020-2021 EDUCATION YEAR E-TWINNING LUCK PROJECT ACTIVITY PLAN -JANUARY
ACTIVITY | D.APPLICATION | MANNER OF APPLICATION | DATE-DEADLINE | PRODUCT
PREPARING PROJECT POSTERS and LOGOS | CANVA POSTERMYWALL | ALL THE PARTNERS CREATE A PROJECT POSTER and LOGO . THE MOST APPEALING ONE IS DECIDED THROUGH A SURVEY BETWEEN ALL THE PARTNERS. | JANUARY 7th | PROJECT POSTERS
SURVEY TO CHOOSE THE PROJECT POSTER and LOGO | DOCS.GOOGLE | THE PROJECT PARTNERS VOTE ON THE PROJECT POSTER and LOGOS | JANUARY 8th | __________
RESULTS ARE ANNOUNCED | TWINSPACE | PROJECT SURVEY RESULTS ARE ANNOUNCED ON TWINSPACE | JANUARY 9th | PROJECT POSTER and LOGO
INTRODUCING THE PROJECT ON SCHOOL WEBSITES | SCHOOL WEBSITES | ALL THE PARTNERS INTRODUCE THE PROJECT ON THEIR SCHOOL WEBSITES VIA A LINK. THEY SHARE PROJECT INTRO VIDEO, LOGO AND POSTER. | JANUARY 10th | ______
INTRODUCING OUR SCHOOLS | BLIPPAR | ALL THE PARTNERS CREATE A VIDEO INTRODUCING THEIR SCHOOLS WITH THE HELP OF THEIR STUDENTS | JANUARY 10-15th | SCHOOL INTRODUCTION VIDEOS
OUR MEMBERS' PROJECT POSTERS and LOGOS | CANVA POSTERMYWALL | ALL THE MEMBERS CREATE A PROJECT POSTER and LOGO . EACH SCHOOL CHOOSE THEIR FAVOURITES THROUGH A SURVEY. | JANUARY 15-22 | STUDENTS' PROJECT POSTERS and LOGOS
DECIDING THE METHODS TO BE USED | TWINSPACE ONLINE MEETING | ALL THE PARTNERS MEET TO DISCUSS THE METHODS AND APPLICATIONS TO BE USED IN DETAILED | JANUARY 23rd | WEBINAR
ANNOUNCING THE METHODS AND APPLICATIONS TO BE USED | TWINSPACE | THE METHODS AND APPLICATIONS TO BE USED ARE SHARED ON TWINSPACE BY THE DUTY HOLDER PARTNER | JANUARY 24th | VOCABULARY LEARNING METHODS
PADLET SCHOOL BOARDS | PADLET | EACH SCHOOL PREPARE THEIR SCHOOL BOARDS WITH THEIR STUDENTS. | JANUARY 25-30 | SCHOOL BOARDS

## FEBRUARY
2020-2021 EDUCATION YEAR E-TWINNING LUCK PROJECT ACTIVITY PLAN -FEBRUARY
ACTIVITY | TOPIC | D.APPLICATION | MANNER OF APPLICATION | DEADLINE | PRODUCT
MNEMONIC | HOBBIES& FREE TIME ACTIVITIES | CRELLO / CANVA/ SKETCHPAD/ PAINT/ POSTERMYWALL | The students create their own imaginative, exaggerated and funny visuals to look like flashcards. | FEBRUARY 1-7 | FUNNY FLASHCARDS
SURVEY | HOBBIES& FREE TIME ACTIVITIES | TWINSPACE FORUM | The students evaluate the process. | FEBRUARY 8th | SURVEY RESULTS
E-SAFETY WEEK | E-SAFETY | ZOOM-NOIZZ PICSART | The members have a webinar on e-safety with a counselor and they create collaborative puzzles. | FEBRUARY 11th | PUZZLE WORKS
MIMING (Listen and Mime) | VERBS | PADLET | The students listen to some stories and make the determined gestures as they hear some specific words. | FEBRUARY 9-16 | VIDEOS
SURVEY | VERBS | TWINSPACE FORUM | The students evaluate the process. | FEBRUARY 17th | SURVEY RESULTS
ABC BRAINSTORMING | JOBS | CRELLO / CANVA/ SKETCHPAD/ POSTERMYWALL | The students reinforce their learning finding a related word for each letter of the alphabet. | FEBRUARY 18-25 | POSTERS
SURVEY | JOBS | TWINSPACE FORUM | The students evaluate the process. | FEBRUARY 26th | SURVEY RESULTS
CALLIGRAMS | TRANSPORTATION | WORDART | The students create some shapes that will look like the meaning of the given words | FEBRUARY 27- MARCH 5 | CALLIGRAMS
SURVEY | TRANSPORTATION | TWINSPACE FORUM | The students evaluate the process. | MARCH 6th | SURVEY RESULTS

## MARCH
2020-2021 EDUCATION YEAR E-TWINNING LUCK PROJECT ACTIVITY PLAN -MARCH
ACTIVITY | TOPIC | D.APPLICATION | MANNER OF APPLICATION | DEADLINE | PRODUCT
ROLE-PLAY | DAILY ACTIVITIES | AVATAR& CHATTER PIX/ PIXTON | The students create their own avatarts and make them speak in a conversation including the target words. | MARCH 7-14 | VIDEOS- COMICS
SURVEY | DAILY ACTIVITIES | TWINSPACE FORUM | The students evaluate the process. | MARCH 15th | SURVEY RESULTS
SNAP WORDS | ANIMALS& ANIMAL FEATURES | CRELLO / CANVA/ SKETCHPAD/ PAINT/ POSTERMYWALL | The students learn the new vocabulary creating funny drawings. | MARCH 16-23 | FUNNY FLASHCARDS
SURVEY | ANIMALS& ANIMAL FEATURES | TWINSPACE FORUM | The students evaluate the process. | MARCH 24th | SURVEY RESULTS
ANTONYMS GAME | ADJECTIVES | CRAM | The students learn the adjectives via entertaining games. | MARCH 25-31 | PHOTOS
SURVEY | ADJECTIVES | TWINSPACE FORUM | The students evaluate the process. | APRIL 1st | SURVEY RESULTS

## APRIL
2020-2021 EDUCATION YEAR E-TWINNING LUCK PROJECT ACTIVITY PLAN -APRIL&MAY
ACTIVITY | TOPIC | D.APPLICATION | MANNER OF APPLICATION | DEADLINE | PRODUCT
PICTURE BRAINSTORMING | MY TOWN | MINDMEISTER/ COGGLE | The students create mindmaps producing related words to the topic. | APRIL 2-8 | MINDMAPS
SURVEY | MY TOWN | TWINSPACE FORUM | The students evaluate the process. | APRIL 9th | SURVEY RESULTS
MINIMAL PAIRS | OVERALL CURRICULUM | LEARNING APPS | The students try to differentiate between similar sounding words. | APRIL 10-16 | VIDEOS
SURVEY | OVERALL CURRICULUM | TWINSPACE FORUM | The students evaluate the process. | APRIL 17th | SURVEY RESULTS
LYRICS TRAINING | OVERALL CURRICULUM | LEARNING APPS | The students listen to some songs and try to fill the missing words. | APRIL 18-24 | VIDEOS
SURVEY | OVERALL CURRICULUM | TWINSPACE FORUM | The students evaluate the process. | APRIL 25th | SURVEY RESULTS
COLLABORATIVE PROJECT WORK | OVERALL CURRICULUM | FLIPBOOK | Every one of our members create a sentence of our collaborative story. | APRIL 26- MAY 1 | STORY
FINAL PROJECT WORK | OVERALL CURRICULUM | ARTSTEP | We create a virtual exhibition of all our works. | MAY 2-8 | VIRTUAL EXHIBITION
SURVEY | OVERALL THE PROCESS | KAHOOT/ QUIZIZZ/TYPEFORM /GOOGLE FORMS | The students,parents and the partners evaluate all the process. | MAY 3rd | SURVEY RESULTS